## Instructions
301 Redirect Mapping Template — Instructions
What is this template?
This spreadsheet helps you plan, track, and implement 301 redirects when migrating your ecommerce store to a new platform. It covers every URL type you need to redirect — products, collections, pages, blogs, and more.
How to use it:
Step 1: Go to the "URL Inventory" sheet and export/list every URL from your OLD platform.
Step 2: In the "Redirect Map" sheet, map each old URL to its new URL on the new platform.
Step 3: Use the "Pre-Launch Checklist" to verify everything before going live.
Step 4: After launch, use the "Post-Migration Audit" sheet to track crawl status and fix issues.
Tips:
• Export your old sitemap.xml — it contains every indexed URL.
• Check Google Search Console for your top-performing pages — prioritise those.
• Test redirects BEFORE switching DNS to the new platform.
• Monitor 404 errors in Search Console for 90 days after migration.
Need help migrating products?
Product Upload (productupload.co) lets you import products from your old store — or any supplier website — directly into Shopify, WooCommerce, Wix, BigCommerce, or Squarespace. No CSV files, no manual data entry. AI-powered descriptions, images, and variants included.
Free template by productupload.co

## URL Inventory
URL Path | Full URL | Page Type | Page Title | Monthly Traffic (est.) | Backlinks | Priority | Notes
/products/blue-cotton-tee | https://oldstore.com/products/blue-cotton-tee | Product | Blue Cotton T-Shirt | 320 | 5 | Critical | Top seller — must redirect
/products/leather-crossbody-bag | https://oldstore.com/products/leather-crossbody-bag | Product | Leather Crossbody Bag | 185 | 12 | Critical | Featured in press — strong backlinks
/collections/summer-sale | https://oldstore.com/collections/summer-sale | Collection/Category | Summer Sale | 890 | 3 | Critical | Seasonal collection — high traffic
/collections/womens-tops | https://oldstore.com/collections/womens-tops | Collection/Category | Women's Tops | 540 | 2 | High
/pages/about-us | https://oldstore.com/pages/about-us | Static Page | About Us | 120 | 8 | High | Links from partner sites
/pages/shipping-policy | https://oldstore.com/pages/shipping-policy | Static Page | Shipping Policy | 65 | 1 | Medium
/blogs/style-guide/summer-outfit-ideas | https://oldstore.com/blogs/style-guide/summer-outfit-ideas | Blog Post | 10 Summer Outfit Ideas | 1200 | 22 | Critical | Top organic page — drives most blog traffic
/blogs/style-guide/how-to-style-a-tote-bag | https://oldstore.com/blogs/style-guide/how-to-style-a-tote-bag | Blog Post | How to Style a Tote Bag | 430 | 7 | High
/pages/contact | https://oldstore.com/pages/contact | Static Page | Contact Us | 90 | 4 | Medium
/pages/size-guide | https://oldstore.com/pages/size-guide | Static Page | Size Guide | 210 | 1 | High | Linked from product pages

## Dashboard
Migration Redirect Dashboard
Redirect Map Summary | Priority Breakdown
Total URLs to Redirect | Critical
Redirects Mapped | High
Redirects Tested | Medium
Redirects Live | Low
Not Started
Issues Found
Pre-Launch Checklist Progress | Post-Migration Audit
Tasks Done | URLs Audited
Tasks In Progress | Correct Redirects
Tasks Not Started | Incorrect/Partial
Tasks Blocked | Indexed on Google

## Redirect Map
Old URL Path | Old Full URL | New URL Path | New Full URL | Redirect Type | Page Type | Priority | Status | Tested? | Notes
/products/blue-cotton-tee | https://oldstore.com/products/blue-cotton-tee | /shop/blue-cotton-t-shirt | https://newstore.com/shop/blue-cotton-t-shirt | 301 | Product | Critical | Tested | Yes
/products/leather-crossbody-bag | https://oldstore.com/products/leather-crossbody-bag | /shop/leather-crossbody-bag | https://newstore.com/shop/leather-crossbody-bag | 301 | Product | Critical | Mapped | No | Keep same slug
/collections/summer-sale | https://oldstore.com/collections/summer-sale | /categories/summer-sale | https://newstore.com/categories/summer-sale | 301 | Collection/Category | Critical | Implemented | Yes
/collections/womens-tops | https://oldstore.com/collections/womens-tops | /categories/womens-tops | https://newstore.com/categories/womens-tops | 301 | Collection/Category | High | Mapped | No
/pages/about-us | https://oldstore.com/pages/about-us | /about | https://newstore.com/about | 301 | Static Page | High | Tested | Yes
/pages/shipping-policy | https://oldstore.com/pages/shipping-policy | /policies/shipping | https://newstore.com/policies/shipping | 301 | Static Page | Medium | Mapped | No
/blogs/style-guide/summer-outfit-ideas | https://oldstore.com/blogs/style-guide/summer-outfit-ideas | /blog/summer-outfit-ideas | https://newstore.com/blog/summer-outfit-ideas | 301 | Blog Post | Critical | Tested | Yes | Top organic page
/blogs/style-guide/how-to-style-a-tote-bag | https://oldstore.com/blogs/style-guide/how-to-style-a-tote-bag | /blog/how-to-style-a-tote-bag | https://newstore.com/blog/how-to-style-a-tote-bag | 301 | Blog Post | High | Not Started | No
/pages/contact | https://oldstore.com/pages/contact | /contact | https://newstore.com/contact | 301 | Static Page | Medium | Mapped | No
/cart | https://oldstore.com/cart |  |  | No Redirect Needed | Cart/Checkout | Low | Mapped | No | Platform handles /cart natively

## Pre-Launch Checklist
# | Task | Category | Details | Status | Owner | Due Date
1 | Export full sitemap from old platform | URL Discovery | Download sitemap.xml or use Screaming Frog to crawl. Include all product, collection, page, and blog URLs. | Not Started
2 | Pull top pages from Google Search Console | URL Discovery | Export Performance report > Pages. Sort by clicks/impressions for last 12 months. These are your Critical priority redirects. | Not Started
3 | Check Google Analytics for top landing pages | URL Discovery | Behaviour > Site Content > Landing Pages. Cross-reference with Search Console data. | Not Started
4 | Identify all backlinked pages | URL Discovery | Use Ahrefs, Moz, or Google Search Console Links report. Any page with external backlinks MUST be redirected. | Not Started
5 | Complete URL Inventory sheet | Mapping | List every URL from the old site in the URL Inventory tab with page type, traffic, and priority. | Not Started
6 | Map all old URLs to new URLs | Mapping | Fill in the Redirect Map sheet. Every old URL should have a corresponding new URL or be marked as No Redirect Needed. | Not Started
7 | Verify new URL structure on staging | Mapping | Confirm every new URL in your map actually exists on the new platform staging site before implementing redirects. | Not Started
8 | Implement redirects on new platform | Implementation | Add redirects via platform settings (Shopify: Settings > Navigation > URL Redirects) or .htaccess/server config. | Not Started
9 | Test all Critical redirects manually | Testing | Visit each Critical old URL and verify it 301s to the correct new URL. Check with curl -I or a redirect checker tool. | Not Started
10 | Test all High priority redirects | Testing | Same process for High priority URLs. | Not Started
11 | Bulk test with Screaming Frog | Testing | Upload old URL list to Screaming Frog in List Mode. Verify all return 301 status and correct destination. | Not Started
12 | Update internal links on new site | Content | Search the new site for any links pointing to old URL patterns. Update them to point directly to new URLs. | Not Started
13 | Update Google Business Profile URL | External | Change your website URL in Google Business Profile to the new domain/URL. | Not Started
14 | Update social media profile links | External | Update links in Instagram, Facebook, TikTok, Pinterest bios and any pinned posts. | Not Started
15 | Notify backlink partners of URL change | External | Email partners with high-value backlinks and ask them to update links (reduces redirect dependency over time). | Not Started
16 | Submit new sitemap to Google Search Console | Post-Launch | Add your new site to GSC if on a new domain. Submit the new sitemap.xml. | Not Started
17 | Monitor 404 errors daily for 2 weeks | Post-Launch | Check GSC Coverage/Pages report for crawl errors. Fix any missed redirects immediately. | Not Started
18 | Compare organic traffic week-over-week | Post-Launch | Watch for traffic drops on key pages. Some fluctuation is normal for 2-4 weeks. | Not Started

## Post-Migration Audit
URL (Old) | URL (New) | HTTP Status | Redirect Destination | Correct? | Google Indexed? | Organic Traffic Change | Issue | Action Needed
/products/blue-cotton-tee | /shop/blue-cotton-t-shirt | 301 | https://newstore.com/shop/blue-cotton-t-shirt | Yes | Pending
/collections/summer-sale | /categories/summer-sale | 301 | https://newstore.com/categories/summer-sale | Yes | Yes | -12% |  | Normal fluctuation — monitor
/blogs/style-guide/summer-outfit-ideas | /blog/summer-outfit-ideas | 404 |  | No | No | -100% | Redirect not implemented | Add redirect immediately — top page
/pages/returns-policy | /policies/returns | 301 | https://newstore.com/policies/returns | Yes | Pending
/collections/new-arrivals | /categories/new-arrivals | 302 | https://newstore.com/categories/new-arrivals | Partial | Pending | -5% | Using 302 instead of 301 | Change to 301 — 302 does not pass link equity